## Project_Query
Spec Query | Solution
How to detect a interrupt? | int_enable, int_mask and int-Priority
what do you mean by output signalling? | out_mode
Configurable output interrupt polarity: active-high or active-low.
Configurable output mode: level or pulse. In pulse mode, pulse width is programmable. | untill all the interrupt are served by the controller the level output will not be deasserted
Signal : int_vector[log2(N) -1:0] | clear
Signal : int_priority[N-1:0][P-1:0] | clear
All registers are accessible via a standard bus interface (e.g., APB, AXI-lite, or custom). | we will use any interface to write to the registers of the DUT
what is the significance of two : level and pulse
If I kept the programmable width more , then doesnt it represent as level only?

## Work_sheet
Activity | Est. Date | act. date
Feature extraction | 15/07 | 15/07
Testbench architecture with component details | 16/07
Test case planning | 16/07
Coverage planning | 16/07
Checker planning | 16/07
Review plan with relevant stakeholders | 16/07

## Feature_Extraction
Sr.No. | Feature | Feature Desciption | Details | How to Verify
1 | Parameterized number of interrupt sources (N) (For E.g.int_in[N-1:0], int_enable[N-1:0], etc.). | You can configure the number of interrupt sources (e.g., 8, 16, 32) during synthesis. | Your testbench must support N-bit wide vectors (int_in[N-1:0], int_enable[N-1:0], etc.). | Run with different values of N (e.g., 8, 16, 32). - Ensure REGISTERS also scales with N. - Check coverage bins exist for all sources. - Functional check: drive all int_in[i] and confirm correct mapping to int_status[i] and int_out.
2 | Enable/Disable control for each interrupt source (int_enable) | can selectively enable or disable interrupt sources using int_enable register. | Drive an interrupt with enable=0 -> output should not assert. Drive an interrupt with enable=1 -> output should assert if not masked. | - Write random values to int_enable. - Drive each interrupt one by one. - Scoreboard: check int_out is asserted only when corresponding int_enable[i]=1. - Functional check: disabled interrupts should not affect int_status. checkers : Checkers should be implemented to confirm the write and read values in the registers
3 | Mask Feature (int_mask) | Even if an interrupt is enabled and asserted, it can be masked using int_mask. | Enable and assert a interrupt, but keep it masked -> int_out is deasserted. Unmask -> int_out should now assert. | - Program int_mask[i]=1 while int_enable[i]=1. - Drive interrupt: expect int_status[i]=1 but int_out=0. - Clear mask and check int_out=1.
4 | Programmable Priority for Each Source | If multiple interrupts are active, the one with the highest priority is selected for output. | Trigger multiple interrupts with different priorities. | feature deferred
5 | Status Register (int_status) | Indicates which interrupt sources are currently pending (1 = interrupt asserted & eligible). | Assert an enabled, unmasked interrupt -> int_status[i] should go high. Clear it using int_clear[i] -> status should go low. | - Drive interrupt → scoreboard expects int_status[i]=1. - Write int_clear[i]=1 → verify int_status[i]=0. - Coverage: each bit of int_status toggled 0→1→0.
6 | Configurable Output Polarity (out_polarity) | Output interrupt can be either active-high or active-low. | Set out_polarity = 1 (active-high) -> int_out should go high when interrupt is pending. Set out_polarity = 0 (active-low) -> int_out should go low for pending interrupt. | - Program out_polarity=1 → check int_out asserts high for pending. - Program out_polarity=0 → check int_out asserts low.
7 | Configurable Output Mode (Level or Pulse) (out_mode) | Level mode: Output stays asserted while interrupt is pending. Pulse mode: Output is a fixed-width pulse when new interrupt is detected. | In pulse mode, Output pulse is generated only once per new pending interrupt. Width matches pulse_width register. In level mode, Output stays asserted until all interrupts are cleared. | - Program out_mode=0 (level). Assert int → check int_out should be high or low according to the polarity - Program out_mode=1 (pulse). Assert int → check pulse (according to pulse width) there should be pulse generated with the given pulse width.
8 | Pulse Width Configurable (pulse_width) | In pulse mode, int_out pulse duration is set via pulse_width. | For E.g., Set pulse_width = 4 -> output should stay high for 4 cycles (or low if active-low). | - Program pulse width with random values. Assert interrupt -> Scoreboard measures pulse width in cycles
9 | Clear Register (int_clear) | Software clears a specific interrupt by writing to this register | Write 1 to int_clear[i] -> int_status[i] should clear. If no more pending interrupts -> int_out should deassert. | - Assert int → check int_status[i]=1. - Write int_clear[i]=1 → check int_status[i]=0. - If active interrupt cleared → int_status[i] = 0.

## What_to_Verify
What to verify | Details on How to verify
Interrupt Detection Logic | If int_in[i] is asserted and enabled and not masked -> int_status[i] becomes 1
If int_clear[i] is written -> int_status[i] clears to 0
Priority Arbitration | If multiple interrupts are pending: | on Hold
The one with the highest priority (lowest number) is selected
int_vector correctly shows the selected index
Output Interrupt Generation (int_out) | In level mode: int_out is asserted continuously while any interrupt is valid
In pulse mode: int_out gives a pulse of correct pulse_width on new interrupt
Output Vector (int_vector) | When int_out is active, int_vector gives index of active interrupt
It corresponds with correct priority and unmasked status

## Test_Plan
Testname | Test Desciption | Status
single_int | Enable only one source, assert it, check int_out, int_status, and int_vector. | done
multiple_ints_same_enabled | Assert multiple sources (check int_out =1 and int_status = int_in ) | done
no_ints | all the sources are deactivated (int_in =0, int_enable='0 and int_mask='0) int_out=0 and int_status=0
pulse_mode_trigger | set pulse mode , assert interrupt and check int_out pulse ( width =1 when new interrupt is detected)
same_ints | drive int_in same multiple times
level_mode_trigger | set level mode , assert interrupt and check int_out ( until pending interrupt exists)
switch_mode | check when switching the modes level and pulse | not valid
same_priority_test | Two or more interrupts have same priority and are asserted together. | deferred
dut_reset_test | Apply DUT reset and check all registers have default values (INT_ENABLE, INT_MASK, INT_STATUS = 0)
reg_read_write | write to the registers and read back the value and check integrity
clear_register | when masked interrupt is there , int_status=1 , try clearing it and check int_status=0
status_register | when masked interrupt is there check int_out = 0 and int_status = 1
multiple_ints_diff_enabled | Don't Enable Every interrupt, assert multiple, expect only that one reflected in int_out | done
all_masked_interrupts | Enable all, mask all, assert inputs ( no int_out expected ) | done
all_enabled_unmasked | Enable & unmask all -> assert multiple -> check int_out | deferred
mask_then_trigger | Mask then trigger (No output expected)
active_high_polarity_level | Trigger high signal on int_in-check polarity (out_mode = level)
active_high_polarity_pulse | polarity = active_high and out_mode = pulse
active_low_polarity_level | Trigger out_polarity = active low and level mode
active_low_polarity_pulse | Trigger out_polarity = active low and pulse mode
active_high_width_test | change the programmable width while the polarity = active_high and check the pulse width
active_low_width_test | change the programmable width while the polarity = active_low and check the pulse width
write_readonly_register | try writing the INT_STATUS reg while it is RO
unknown_value_reg | Try writing the x value to the registers and check the behaviour

## DUT_ISSUES
ISSUE | PROBLEM | SOLUTION
assign int_status = pending | dut was counting masked[i] with considering int_mask which should not be there , int_status only requires int_in and int_enable | changed to int_status = int_in & int_enable